## Filled Example
Mental Health Support OKR Tracker
Editable OKR Template · profit.co · Education · Operations · Student Success
|  | Department: Operations · Student Success |  |  | Quarter: Q4 2026
Overall OKR Score (auto-calculated) |  |  |  | 0.49444
Pre-filled worked example (Q4 2026). Plan = target, Actual = current; Progress and Lifecycle Status calculate automatically. Status: Not Started · In Trouble (<30%) · At Risk (30–59%) · On Track (60–99%) · Completed (100%). Overall OKR Score is also calculated on a scale of 0 to 1 (1.00 = 100%, 0.50 = 50%, 0.10 = 10%).
Name | Period | Owner(s) | Type | Progress | Lifecycle Status | Plan | Actual
O1: Connect students to support before well-being affects persistence | Q4-2026 | Rachel Moore |  | 51.67% | At Risk | 100 | 51.6667
KR1.1 Increase share of at-risk students reached by proactive well-being outreach from 40% to 68% | Q4-2026 | Rachel Moore | ↑ Outreach reach | 61% | On Track | 63 | 57.08
KR1.2 Reduce well-being-related stop-out rate (students citing mental health as a reason for leaving) from 9% to 4% | Q4-2026 | James Carter | ↓ Stop-out rate | 44% | At Risk | 7 | 6.8
KR1.3 Keep the average time to connect flagged students to a support resource at or below 3 business days | Q4-2026 | Emily Walsh | ≤ Time to connect | 50% | At Risk | 5 | 6
O2: Build a campus-wide support and referral network | Q4-2026 | Daniel Brooks |  | 43.33% | At Risk | 100 | 43.3333
KR2.1 Increase faculty and staff completion of mental health first-aid / gatekeeper training from 25% to 65% | Q4-2026 | Daniel Brooks | ↑ Gatekeeper training | 45% | At Risk | 55 | 43
KR2.2 Increase share of well-being referrals that receive a warm handoff (not just a referral) from 35% to 65% | Q4-2026 | Laura Jensen | ↑ Warm handoff rate | 22% | In Trouble | 55 | 41.6
KR2.3 Increase peer well-being program (wellness ambassadors) active volunteer rate from 8% to 22% | Q4-2026 | Michael Turner | ↑ Peer volunteer rate | 63% | On Track | 18 | 16.82
O3: Strengthen well-being as a foundation for persistence | Q4-2026 | Amanda Foster |  | 53.33% | At Risk | 100 | 53.3333
KR3.1 Increase well-being check-in completion rate among first-year students from 30% to 60% | Q4-2026 | Amanda Foster | ↑ First-year check-ins | 60% | On Track | 52 | 48
KR3.2 Increase share of students who know how to access campus support when they need it from 55% to 80% | Q4-2026 | Christopher Hall | ↑ Support-access awareness | 0% | Not Started | 72 | 55
KR3.3 Hold the one-year persistence rate of students who engaged well-being support at or above 84% | Q4-2026 | Sarah Bennett | ≥ Support-engaged persistence | 100% | Completed | 80 | 84

## Blank Template
Mental Health Support OKR Tracker
Editable OKR Template · profit.co · Education · Operations · Student Success
Company: |  | Department: |  |  | Quarter:
Overall OKR Score (auto-calculated)
ℹ Enter your objective text in the O1/O2/O3 rows. Fill in each KR row with Name, Owner, Type, Plan, and Actual — Progress and Lifecycle Status calculate automatically.
Name | Period | Owner(s) | Type | Progress | Lifecycle Status | Plan | Actual
O1:
KR1.1
KR1.2
KR1.3
O2:
KR2.1
KR2.2
KR2.3
O3:
KR3.1
KR3.2
KR3.3