## Filled Example
Downtime Reduction OKR Tracker
Editable OKR Template · profit.co · Manufacturing · Operations · Production
|  |  | Department: Operations · Production |  |  | Quarter: Q3 2026
Overall OKR Score (auto-calculated) | [5 empty] | 0.44831
Pre-filled worked example (Q3 2026). Plan = target, Actual = current; Progress and Lifecycle Status calculate automatically. Status: Not Started · In Trouble (<30%) · At Risk (30–59%) · On Track (60–99%) · Completed (100%). Overall OKR Score is also calculated on a scale of 0 to 1 (1.00 = 100%, 0.50 = 50%, 0.10 = 10%).
Name | Period | Owner(s) | Type | Progress | Lifecycle Status | Plan | Actual
O1: Reduce total unplanned downtime and stoppage frequency plant-wide | Q3-2026 | Garrett Holloway |  | 68.71% | On Track | 100 | 69
Keep unplanned downtime at or below 38 minutes per machine per day | Q3-2026 | Garrett Holloway | ≤ Unplanned downtime | 62.5% | On Track | 50 | 47
Reduce minor-stop frequency from 180 to 70 stops per day | Q3-2026 | Hugo Marchetti | ↓ Minor-stop frequency | 43.64% | At Risk | 120 | 132
Raise equipment availability from 58% to 100% of scheduled time | Q3-2026 | Claire Ashworth | ↑ Equipment availability | 100% | Completed | 84 | 100
O2: Attack root causes and speed up breakdown response | Q3-2026 | Claire Ashworth |  | 22.92% | In Trouble | 100 | 23
Raise the share of breakdowns with a completed root-cause analysis from 42% to 100% | Q3-2026 | Claire Ashworth | ↑ Breakdowns with completed RCA | 46.55% | At Risk | 80 | 69
Reduce mean time to repair (MTTR) from 95 to 50 minutes | Q3-2026 | Owen Radcliffe | ↓ Mean time to repair | 22.22% | In Trouble | 72 | 85
Keep open critical-spares stockout gaps to no more than 1 | Q3-2026 | Owen Radcliffe | ≤ Open critical-spares gaps | 0% | Not Started | 3 | 5
O3: Shrink planned-stop losses and build frontline maintenance capability | Q3-2026 | Denise Falk |  | 42.86% | At Risk | 100 | 43
Hold preventive-maintenance effectiveness (PM-caught vs breakdown) between 62% and 70% | Q3-2026 | Claire Ashworth | ↔ PM effectiveness | 41.67% | At Risk | 55 | 48
Hold autonomous-maintenance coverage at or above 95% of lines | Q3-2026 | Denise Falk | ≥ Autonomous-maintenance coverage | 25% | In Trouble | 80 | 65
Raise TPM-step completion across operators from 48% to 90% | Q3-2026 | Denise Falk | ↑ TPM-step completion | 61.9% | On Track | 72 | 74

## Blank Template
Downtime Reduction OKR Tracker
Editable OKR Template · profit.co · Manufacturing · Operations · Production
Company: |  |  | Department: |  |  | Quarter:
Overall OKR Score (auto-calculated)
ℹ Enter your objectives, then each KR's Owner, Type, Plan (this period's checkpoint) and Actual (current value). Progress and Lifecycle Status calculate automatically.
Name | Period | Owner(s) | Type | Progress | Lifecycle Status | Plan | Actual
O1: | [6 empty] | 0
KR1.1
KR1.2
KR1.3
O2: | [6 empty] | 0
KR2.1
KR2.2
KR2.3
O3: | [6 empty] | 0
KR3.1
KR3.2
KR3.3